## Form 4
Tender Analysis | [6 empty] | Tenderer 1 |  |  | Tenderer 2 |  |  | Tenderer 3 |  |  | Tenderer 4
Procurement Package: Samson Bridge |  |  |  |  | Supplier Name |  | Robemen |  |  | Lamlian |  |  | Cordem |  |  | Densol
Procurement Package No.: 1982 |  |  |  |  | Quotation received
Item | Description | Unit | Procurement Budget |  |  | Procurement Quantity | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Analysis | Analysis
|  |  | Budget Quantity (A) | Budget Rate (B) | Budget Total (A)*(B) | (C) | (D) | (C)*(D) |  | (E) | (C)*(E) |  | (F) | (C)*(F) |  | (G) | (C)*(G) |  | Min Rate | Min Total
A | Preliminaries
A.1 | Mobilisation | ea | 1 |  |  | 1
A.2 | Demobilisation | ea | 1 |  |  | 1
A.3 | Supervision | ea | 1 |  |  | 1
SUBSTRUCTURE
1 | Mass Concrete Blinding Layer
1a | Abutment Headstocks | m3 | 5 | 323 | 1615 | 5 | 404.8 | 2024 |  | 423 | 2115 |  | 467 | 2335 |  | 550 | 2750
2 | Placement of Concrete including False works/Scaffolding, Access Stairs, Scabble, Form, Finish & Cure |  |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0
(a) | Abutment Headstocks | m3 | 135 | 1400 | 189000 | 135 | 1673 | 225855 |  | 1654 | 223290 |  | 1787 | 241245 |  | 1850 | 249750
(b) | Pile Caps - Pier 1 & 2 - Dry | m3 | 130 | 265.54 | 34520.2 | 130 | 357.84 | 46519.2 |  | 382.22 | 49688.6 |  | 412.87 | 53673.1 |  | 1100 | 143000
(bb) | Pile Caps - Pier 3 to 9 -Wet - Precast Shell Infill | m3 | 728 | 267 | 194376 | 728 | 330.91 | 240902.48 |  | 304.98 | 222025.44 |  | 350.65 | 255273.2 |  | 1300 | 946400
(c) | Pier Columns - P1 & P2 - Dry | m3 | 85 | 442.54 | 37615.9 | 85 | 542.46 | 46109.1 |  | 500 | 42500 |  | 532.65 | 45275.25 |  | 900 | 76500
(cc) | Pier Columns - P3 to P9 - Wet | m3 | 192 | 596.51 | 114529.92 | 192 | 596.51 | 114529.92 |  | 610.2 | 117158.4 |  | 643.65 | 123580.8 |  | 1200 | 230400
(d) | Pier Headstocks - P1 & P2 - Dry | m3 | 97 | 744.63 | 72229.11 | 97 | 744.63 | 72229.11 |  | 800 | 77600 |  | 852.86 | 82727.42 |  | 1250 | 121250
(dd) | Pier Headstocks - P3 to P9 - Wet | m3 | 435 | 813.58 | 353907.3 | 435 | 813.58 | 353907.3 |  | 782.87 | 340548.45 |  | 822.67 | 357861.45 |  | 1650 | 717750
3 | Supply and Placement of Reinforcement |  |  |  | 0 | [11 empty] | 0
(a) | Abutment Headstocks | t | 22.01 | 1343.56 | 29571.7556 | 22.01 | 1557.38 | 34277.9338 |  | 1765 | 38847.65 |  | 1799.54 | 39607.8754 |  | 4356.76 | 95892.2876
(b) | Pile Caps - Dry | t | 30 | 1343.56 | 40306.8 | 30 | 1557.38 | 46721.4 |  | 1765 | 52950 |  | 1799.54 | 53986.2 |  | 1200 | 36000
(bb) | Pile Caps - Wet | t | 87 | 1343.56 | 116889.72 | 87 | 1557.38 | 135492.06 |  | 1765 | 153555 |  | 1799.54 | 156559.98 |  | 1500 | 130500
(c) | Pier Columns - Dry | t | 17 | 1343.56 | 22840.52 | 17 | 1557.38 | 26475.46 |  | 1765 | 30005 |  | 1799.54 | 30592.18 |  | 900 | 15300
(cc) | Pier Columns - Wet | t | 54 | 1343.56 | 72552.24 | 54 | 1557.38 | 84098.52 |  | 1765 | 95310 |  | 1799.54 | 97175.16 |  | 1200 | 64800
(d) | Pier Headstocks - Dry | t | 20 | 1712 | 34240 | 20 | 1816.95 | 36339 |  | 1954 | 39080 |  | 2000.65 | 40013 |  | 1200 | 24000
(dd) | Pier Headstocks - Wet | t | 88 | 1712 | 150656 | 88 | 1816.95 | 159891.6 |  | 1954 | 171952 |  | 2200.45 | 193639.6 |  | 1500 | 132000
4 | Installation of Precast Pier Pile Cap Shell Including Steel Bracket Assemblies | each | 9 | 8874 | 79866 | 9 | 8972.5 | 80752.5 |  | 10766.5 | 96898.5 |  | 11965.65 | 107690.85 |  | 2500 | 22500
[5 empty] | 0 | [8 empty] | 0 |  |  | 0
| COMPLETION OF SUPERSTRUCTURE |  |  |  | 0 | [8 empty] | 0 |  |  | 0
5 | Placement of Concrete including False works/Scaffolding, Access Stairs, Scabble, Form, Finish & Cure |  |  |  | 0 | [11 empty] | 0
(a0) | Place Concrete into diaphragm beams / cross girders | m3 | 100 | 2565 | 256500 | 100 | 2783.36 | 278336 |  | 2894.56 | 289456 |  | 2965.09 | 296509 |  | 4000 | 400000
(a00) | Place Concrete into Link Slabs - 3.2m wide | m3 | 95 | 2000 | 190000 | 95 | 2381.09 | 226203.55 |  | 2500 | 237500 |  | 2456.98 | 233413.1 |  | 1500 | 142500
(a1) | Deck slab - Allow Bracket & Walkway along both sides of bridge | m | 660 | 703.56 | 464349.6 | 660 | Excl. | Excl. |  | 1200 | 792000 |  | 603 | 397980 |  | Missing | missing
(a2) | Place Permanent Form 24mm Cement Fibre Sheeting - Category 5 | m2 | 1300 | 60 | 78000 | 1300 | 64.89 | 84357 |  | 70 | 91000 |  | 80 | 104000 |  | 45 | 58500
(a3) | Seal Gaps between Super tees with 300 wide Bitac | m | 900 | 13.45 | 12105 | 900 | 12.98 | 11682 |  | 14.65 | 13185 |  | 18.87 | 16983 |  | 18 | 16200
(a4) | Form Construction Joints - Deck Slab | m2 | 150 | 32 | 4800 | 150 | 30.08 | 4512 |  | 35.98 | 5397 |  | 46.87 | 7030.5 |  | 400 | 60000
(a5) | Form Stop Ends - Deck Slab | m2 | 55 | 100 | 5500 | 55 | 164.9 | 9069.5 |  | 170.43 | 9373.65 |  | 243.76 | 13406.8 |  | 250 | 13750
(a6) | Scabble Construction Joints - Deck Slab | m2 | 150 | 25 | 3750 | 150 | 17.1 | 2565 |  | 21.7 | 3255 |  | 30.045 | 4506.75 |  | incl.
(a7) | Blow out before pouring concrete - Deck Slab | m2 | 1200 | 22 | 26400 | 1200 | incl. | incl. |  | 20 | 24000 |  | Exl | Exl |  | 20 | 24000
(a8) | Place Concrete to Deck Slab | m3 | 1200 | 123.54 | 148248 | 1200 | 135.22 | 162264 |  | 156.76 | 188112 |  | 187.45 | 224940 |  | 350 | 420000
(a9) | Finish & Cure Deck Slab | m2 | 5610 | 8 | 44880 | 5610 | incl. | incl. |  | 15 | 84150 |  | 13 | 72930 |  | incl.
(b) | Stitch Pour for Concrete Barrier including Scabbling, Form & Finishing Concrete | m3 | 35 | 1989.21 | 69622.35 | 35 | 1989.21 | 69622.35 |  | 2154.2 | 75397 |  | 2645.67 | 92598.45 |  | 200 | 7000
(c) | Cast In-Situ Concrete Traffic Barrier including Scabbling, Form and Finish Concrete | m3 | 97 | 2256.45 | 218875.65 | 97 | 2657.71 | 257797.87 |  | 2876.76 | 279045.72 |  | 3124.56 | 303082.32 |  | Missing | Missing
6 | Supply and Placement of Reinforcement to Deck Slab and Barriers | t | 326 | 1190 | 387940 | 326 | 1318.65 | 429879.9 |  | 1234 | 402284 |  | 1543.45 | 503164.7 |  | 1350 | 440100
7 | Install Bondek 1.0 BMTon Footway | m2 | 658 | 129.78 | 85395.24 | 658 | 129.78 | 85395.24 |  | 165.76 | 109070.08 |  | 187.45 | 123342.1 |  | Missing | Missing
8a | Cast In-Situ Concrete on Footway | m3 | 150 | 405.6 | 60840 | 150 | 413.83 | 62074.5 |  | 398.86 | 59829 |  | 565.45 | 84817.5 |  | 900 | 135000
[5 empty] | 0 | [11 empty] | 0
| APPROACH SLABS |  |  |  | 0 | [11 empty] | 0
9 | Mass Concrete to Approach Slab | m3 | 9 | 438.96 | 3950.64 | 9 | 438.96 | 3950.64 |  | 500.87 | 4507.83 |  | 587.34 | 5286.06 |  | 550 | 4950
10 | Supply and Placement of Concrete in Approach Slabs | m3 | 64 | 199.89 | 12792.96 | 64 | 199.89 | 12792.96 |  | 253.67 | 16234.88 |  | 265.34 | 16981.76 |  | 1500 | 96000
11 | Supply and Place Reinforcement | t | 22 | 1158.6 | 25489.2 | 22 | 1158.6 | 25489.2 |  | 1342 | 29524 |  | 1764.3 | 38814.6 |  | 1350 | 29700
[5 empty] | 0 | [11 empty] | 0
| MISCELLANEOUS |  |  |  | 0 | [11 empty] | 0
12 | FRP Maintenance and Access Stair, Landings, Access Platforms (Including Associated Handrails) | each | 2 | 20917 | 41834 | 2 | 20917 | 41834 |  | Excl | Excl |  | 19182.5 | 38365 |  | 15000 | 30000
| Total for Package 1982 |  |  |  | 3644155.1056 |  |  | 3473950.2938 |  |  | 4466845.2 |  |  | 4459387.7054 |  |  | 4886492.2876 |  |  | #REF!
Item | Additional Items | Unit | Procurement Budget |  |  | Procurement Quantity | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Analysis | Analysis
|  |  | Budget Quantity (A) | Budget Rate (B) | Budget Total (A)*(B) | (C) | (D) | (C)*(D) |  | (E) | (C)*(E) |  | (F) | (C)*(F) |  | (G) | (C)*(G) |  | Min Rate | Min Total
2 | Additional Items
2.01
2.02
| Total Additional Items |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | #REF!
Item | Subcontractor Exclusions | Unit | Procurement Budget |  |  | Procurement Quantity | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ |  | Analysis | Analysis
|  |  | Budget Quantity (A) | Budget Rate (B) | Budget Total (A)*(B) | (C) | (D) | (C)*(D) |  | (E) | (C)*(E) |  | (F) | (C)*(F) |  | (G) | (C)*(G) |  | Min Rate | Min Total
3 | Subcontractor Exclusions
3.01 | [6 empty] | Deck slab - Allow Bracket & Walkway along both sides of bridge | 398654.98 |  | FRP Maintenance and Access Stair, Landings, Access Platforms (Including Associated Handrails) | 38365 |  | Blow out before pouring concrete - Deck Slab | 25000
3.02
3.03
| Total Subcontractor Exclusions |  |  |  | 0 |  |  | 398654.98 |  |  | 38365 |  |  | 25000 |  |  | 0 |  |  | 0
| Total Adjusted Submission | [6 empty] | 3872605.2738 |  |  | 4505210.2 |  |  | 4484387.7054 |  |  | 4886492.2876 |  |  | 3872605.2738
| Total Budget |  |  |  | 3644155.1056
| Gain/ Loss Against Budget | [6 empty] | -228450.1682 |  |  | -4505210.2 |  |  | -4484387.7054
| Gain/ Loss Against Budget Percentage | [6 empty] | -6.269% |  |  | -123.6% |  |  | -123.1% |  |  | 0%
Comment(s):
1 | For quotes that have already been reviewed and entered, the following conditions apply:
2 | Work areas to be cleared prior to commencement of works
3 | Sedimentation control, clean up required after inclement weather, treatment of soils and dewatering of working area is client's responsibilites.
4 | Pricing is based upon continuous uninterrupted work being available from commencements to completion
5 | Maximum defect liability Period: 12 months at completion of works
6 | Contract program to be agreed and discussed prior to award
7 | Inclusions and Exclusions listed (excluding scope of works) under the Exclusions and Inclusions Heading of Densol Quote also apply for the rest of the quotations
8
9

## 040 Crash Cushion - Hire (hidden)
Tender Analysis |  |  |  |  | Supplier 1 |  |  | Supplier 2 |  |  | Supplier 3 |  |  | Supplier 4 |  |  | Supplier 5
Procurement Package: 040 |  |  | Supplier Name |  | Ingal Civil Products (CZ QuadGuard) |  |  | Australian Construction Products (TAU-II) |  |  | LB Australia Pty Ltd (Smart Cushion SCI100) |  |  | Evolution Civil (CZ Quadguards) |  |  | Coates Hire (TAU/Quad Crash Cushion)
Procurement Package No.: Safety Crash Cushion |  |  | Quotation received
Item | Hire and Install |  | Quantity | Unit | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Analysis | Analysis
|  |  | (A) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | Min Rate | Min Total
1 | Hire Option
1.01 | Supply (Hire) traffic crash cushion - 80km speed rating (20no. units) for Asphalt |  | 16140 | days | Not Priced | Not Priced | [insert) | 32 | 516480 | [insert) | 41 | 661740 | [insert) | Not Priced | Not Priced | [insert) | 22.5 | 363150 | TAU/Quad Crash Cushion 80km | 22.5 | 363150
1.02 | Installation materials |  | 20 | no | Not Priced | Not Priced |  | incl | incl |  | excl. | excl. |  | Not Priced | Not Priced |  | 600 | 12000 |  | 600 | 12000
1.03 | Installation of traffic crash cushion |  | 20 | no | Not Priced | Not Priced |  | 2486 | 49720 |  | excl. | excl. |  | Not Priced | Not Priced |  | 1900 | 38000 |  | 1900 | 38000
| Total Hire Option: |  |  |  |  | 0 |  |  | 566200 |  |  | 661740 |  |  | 0 |  |  | 413150 |  |  | 413150
Item | Additional Hire Items |  | Quantity | Unit | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Analysis | Analysis
|  |  | (A) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | Min Rate | Min Total
2 | Additionl Items
2.01 | Supply traffic (Hire) crash cushion - 80km speed rating (20no. units) for Non Asphalt |  |  |  | N/A |  |  | 29 |  |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2.02 | Supply (Hire) ABSORB 350 hire |  |  |  | N/A |  |  | 25 |  |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2.03 | Damage Waiver |  |  |  | N/A | [5 empty] | N/A | N/A |  | N/A | N/A |  |  | 46893.75
| Total Additional Hire Items |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 46893.75
Item | Subcontractor Exclusions |  | Quantity | Unit | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Analysis | Analysis
|  |  | (A) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | Min Rate | Min Total
Subcontractor Exclusions (Provisional Allowances in Red)
1.02 | Installation materials |  | 20 | Prov. Sum | Not Priced | Not Priced | [insert) | incl | incl | [insert) | 600 | 12000 | [insert) | Not Priced | Not Priced | [insert) | incl | incl | [insert)
1.03 | Installation of traffic crash cushion | [insert) | 20 | Prov. Sum | Not Priced | Not Priced |  | incl | incl |  | 2000 | 40000 |  | Not Priced | Not Priced |  | incl | incl
| Total Subcontractor Exclusions |  |  |  |  | 0 |  |  | 0 |  |  | 52000 |  |  | 0 |  |  | 0
Item | Risk and Opportunities |  | Quantity | Unit | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Rate ($/unit) | Total $ | Comments | Analysis | Analysis
|  |  | (A) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | (B) | (A)*(B) |  | Min Rate | Min Total
| Total Risk and Opportunities |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Total Adjusted Submission | [7 empty] | 566200 |  |  | 713740 | [5 empty] | 413150 |  |  | 413150
| 413150 | Lowest Price |  |  | N/A |  |  | 137% |  |  | 172.8% |  |  | N/A |  |  | 100%
|  |  | Rank |  | N/A |  |  | 2 |  |  | 3 |  |  | N/A |  |  | 1
Comment(s):
1
2
3
4
5